## 1. Overview
Video Tour Website
Price and plan · 28 July 2026 · Twelve space studios
WHAT YOU GET
The website | A website for your property built around one video. When a visitor taps a menu item, the video flies them to that part of the property and stops there. The page never reloads.
Why it helps | People watch instead of scrolling. They stay longer, see more, and are more likely to call you.
How it runs | The site is made of simple files served from the internet's fastest network. There is no server to rent and nothing that can crash.
Works on | iPhone, Android, iPad, laptop and desktop. On a slow network it shows photos instead of video, so the site still works.

## 2. How It Works
How it works
Step | What the visitor sees | What they do
1 Opens the site | The video starts playing on its own. No sound. No play button. The project name fades in. | Just watches
2 Video stops | The video stops on a nice frame. That frame stays on screen as the background. A menu bar appears at the bottom. | Reads the menu, taps one
3 Camera flies | The camera flies to that part of the property. It takes 2 to 3 seconds. | Watches. Taps do not work during the flight.
4 Menu opens | A clear glass panel slides in from the right. It lists what is in that area. For example: Gym, Pool, Lounge. | Taps one item
5 Photos open | Photos of that room fill the screen. Small round buttons on the left switch between View 1, View 2, View 3. | Swipes through the photos
6 360° view | If that room has a 360° photo, a button appears. Tapping it lets them look all around the room. | Drags to look around, pinches to zoom
7 Floor plans | Tabs for each flat type. Built-up area and facing. They can zoom into the drawing. | Compares the flats
8 Map | A map with pins for schools, hospitals, metro and malls. Each pin shows the drive time. | Checks what is nearby
9 Back to start | Tapping home takes them back to the first frame. | Explores another area
10 Contact | A WhatsApp or call button so they can reach you. | Calls or messages you

## 3. Tools Used
Tools used
Every tool here is free. Nothing charges you per visitor. You will never get a surprise bill.
Part | Tool | Why | Cost
Website base | Next.js | A well known tool used by big companies. It makes plain files that can be hosted anywhere for free. | Free
Code safety | TypeScript | Catches mistakes before the site goes live, not after. | Free
Look and feel | Tailwind CSS | Fast to style and easy for any developer to pick up later. | Free
Smooth motion | GSAP | Makes the panels slide in smoothly, like a film. | Free
Video | Built into the browser | One video file. No video hosting bill, no per-minute charge. | Free
360° view | three.js | Wraps the 360° photo around the viewer. Custom touch controls so it feels right on a phone. | Free
Floor plans | Zoom and pan tool | Pinch to zoom works properly on mobile. | Free
Map | Mapbox with free map tiles | Google Maps charges per map view and needs a credit card. This does not. | Free
Icons | Lucide | Clean, simple icon set. | Free
Fonts | Google Fonts | Served from your own site, so it loads fast. | Free
Video processing | FFmpeg | Shrinks your video for the web without losing quality. | Free
Hosting | Cloudflare Pages | Free plan. Fast worldwide. Free HTTPS lock. | Free
Code storage | GitHub, private | Your code is safe and it becomes yours once everything completed. | Free
No tool on this list has a monthly fee. Your only bill is the domain name, about ₹800 to 1200 a year.

## 4. Work
The work, day by day
15 days of work in total. Each line is a piece of the job. One day is 8 hours of real work.
| Task | What is done | Days
1 | Kickoff and planning | Agree the menu structure, collect all your photos, video, plans and text. | 1
2 | Setup and your branding | Set up the project, apply your logo, colours and fonts. | 1
3 | Video engine | Make the video fly to the right place and stop cleanly. Handle slow networks. Make sure taps do not break it mid-flight. | 2.5
4 | Menus | Bottom menu bar and the sliding side panel, filled with your real menu items. | 1
5 | Photo gallery | Full screen photos for each room, with the view switcher. | 1
6 | 360° viewer | Connect your 360° photos so visitors can look around each room. | 1
7 | Floor plans | Tabs for each flat type, with area and facing details, and pinch to zoom. | 1
8 | Location map | Map with your pins and drive times. | 1
9 | Video and photo processing | Shrink the video for fast loading, and mark the exact time point for every menu item. | 1
10 | Mobile and accessibility | Make it work well on small screens. Make it usable with a keyboard. | 1
11 | Google and WhatsApp sharing | Page title, search description, WhatsApp share picture, RERA number and disclaimer. | 0.5
12 | Testing on real phones | Test on a real iPhone and a real Android. Fix what breaks. | 1
13 | Launch | Put it live on your domain. | 0.5
| Total |  | 13.5
NOT IN THIS PRICE — WE CAN ADD THESE LATER
Feature |  | Why it is not included now | Days
Enquiry form |  | A form needs a small backend. A WhatsApp button does the same job for free, so we use that first. | 2
Clickable dots on the video |  | Nice to have, but the menu already gets people everywhere. Saves 2 days now. | 2
Brochure download with email capture |  | Add it once you know people are actually visiting. | 1.5
CRM connection |  | Only worth it once you have steady leads coming in. | 3
Extra language |  | Per language. You give me the translation. | 2
Extra 360° photo |  | Per photo, beyond the six included. | 0.5

## 5. Price
Price
All amounts in Rupees.
WHAT YOU PAY
Item | Amount | Notes
Days of work | 13.5 | The full list is on sheet 4.
Total price | 25000 | One fixed price for the whole website. Nothing else to pay me.
HOW YOU PAY
When | Amount | What has happened by then
On starting | 7500 | You confirm, you send me all your photos and video, and I begin the same day.
On launch | 17500 | The site is live on your domain, you are trained on the admin page, and the code is yours.
Total | 25000
The 30% on starting is mainly so we both take the dates seriously. .
IF YOU SEND MORE THAN WE AGREED
Extra | Price | Why
Every 10 extra photos | 500 | Over the 60 included. Each photo has to be resized, renamed and linked.
Every extra 360° photo | 1000 | Over the 6 included. Each one needs checking and connecting.
Every extra menu item | 500 | Over the 5 included. Each one needs its own video time point.
Every extra floor plan type | 1000 | Over the 3 included.
Video longer than 90 seconds | 2000 | A longer video means re-compressing and re-marking every time point.
A third round of changes | 2000 | Two rounds are included. This is per extra round.
These are fixed prices, agreed before I do the extra work. Nothing is ever added to your bill without you saying yes first. Sending more files does not increase your hosting cost — that stays free. See sheet 6.
WHAT IS NOT IN THIS PRICE
Contact form, brochure download

## 6. Yearly Costs
Yearly costs
These are not part of my price. You pay these directly. I have picked the cheapest option each time.
Item | Where from | How often | Cost a year
MUST HAVE — THE SITE CANNOT GO LIVE WITHOUT THESE
Domain name | Cloudflare or Namecheap. A .in domain is the cheapest. | Yearly | 800-1200
Hosting | Cloudflare Pages. Free plan is enough for you. | Yearly | 0
HTTPS lock | Comes free with the hosting. Set up automatically. | Yearly | 0
Data for the video | Included free in the hosting plan. | Yearly | 0
Domain settings | Cloudflare. Free. | Yearly | 0
Total you must pay each year |  |  | 0
ONLY IF YOU GROW — NOT NEEDED NOW
Bigger hosting plan | Only if you cross about 10,000 visitors a month. | Yearly | 0
Backend for a contact form | Cloudflare Workers. Free plan covers far more than you will need. | Yearly | 0
SUPPORT AFTER LAUNCH
Free fixes | Anything broken in the first 30 days after launch, I fix free. | One time | 0
Later changes | Quoted as a fixed price before I start. Only when you ask. | As needed | 0
WHAT IT COSTS YOU IN TOTAL
Year 1 | The website, plus the domain name. |  | 25000
Year 2 and after | Just the domain renewal. Nothing else. |  | 0
IF YOU ADD MORE PHOTOS OR VIDEOS LATER
Question | Answer |  | Extra cost
More visitors to the site? | Costs nothing extra. The hosting plan has no limit on visitors or data. Ten people or ten thousand, the price is the same. |  | 0
More photos? | Costs nothing extra. Photos are small. Two hundred photos is still well inside the free plan. |  | 0
More 360° photos? | Costs nothing extra. Each one is about 3 MB. |  | 0
A longer video? | Costs nothing extra to host, but one rule matters: any single file must stay under 25 MB. I compress the video to fit. If it still will not fit, I move it to Cloudflare R2, which is also free. |  | 0
A second property later? | Costs nothing extra to host. It would be a new website, quoted separately. |  | 0
Note on C22: No yearly maintenance contract. You only pay when you actually want a change.

## 7. Timeline
15 day plan
15 working days, about 3 weeks. Day 1 starts only when I have all your files.
Stage | What is finished | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Kickoff and files | Menu agreed, all your files received | bar: 1
Setup and branding | Your logo, colours and fonts are in | bar: 2
Video engine | Camera flies and stops cleanly on a phone | bar: 3 to 5
Menus | Bottom bar and side panel working with your items | bar: 5 to 6
Photos and 360° | Gallery and look-around view working | bar: 6 to 7
Floor plans and map | Both sections working | bar: 8
Your real video and photos | Video shrunk, all time points marked | bar: 10 to 11
Mobile and sharing | Works on small screens, WhatsApp preview ready | bar: 12
Testing on real phones | Tested on a real iPhone and a real Android | bar: 13 to 14
Launch | Live on your domain | bar: 15